## time costs
date | expenditure of time in hours | Paul | Kevin | Maxi | Phil | done | to do | open points | comments
2014-01-21 | 2.75 | x | x | x | x | specify requirements in general
2014-01-22 | 1 | x | x | x | x | meeting with client | evaluation of technology; activity diagram, data model
2014-01-23 | 3.75 | x | x | x | x | Datamodel, Activity Diagram
2014-01-31 | 4.5 |  | x | x | x | Enhancement Data Model & Activity Diagram, Technology check "Appguyver, steroids" | simple custom quizduell app with steroids-technology
2014-02-04 | 3 | x |  | x | x | steroids evaluation | serverinterface definition, technology decision, GUI Prototyping
2014-02-06 | 6 | x | x | x | x | GUI Prototypeing, Decision PHONEGAP Prototype (REQ), Server Interface | technology decision, phonegap prototype development, server core functionality development
2014-02-19 | 4 | x | x | x | x | GUI development
2014-02-24 | 4.5 | x |  | x | x | GUI development | NeuesSpielScreen, Home