## time costs
date | expenditure of time in hours | Paul | Kevin | Maxi | Phil | done | to do | open points | comments
2014-01-21 | 2.75 | x | x | x | x | specify requirements in general
2014-01-22 | 1 | x | x | x | x | meeting with client | evaluation of technology; activity diagram, data model
2014-01-23 | 3.75 | x | x | x | x | Datamodel, Activity Diagram
2014-01-31 | 4.5 |  | x | x | x | Enhancement Data Model & Activity Diagram, Technology check "Appguyver, steroids" | simple custom quizduell app with steroids-technology
2014-02-04 | 3 | x |  | x | x | steroids evaluation | serverinterface definition, technology decision, GUI Prototyping
2014-02-06 | 6 | x | x | x | x | GUI Prototypeing, Decision PHONEGAP Prototype (REQ), Server Interface | technology decision, phonegap prototype development, server core functionality development
2014-02-19 | 4 | x | x | x | x | GUI development
2014-02-24 | 4.5 | x |  | x | x | GUI development | NeuesSpielScreen, Home
2014-02-26 | 5 |  | x | x | x | Server Connection randomCategoriesFor, Mark Answers, Local Storage |  | Character limitation frage screen Navigation via pop&push (Back on Frage 2 Screen goes to Rundenübersicht, not to Frage 1)
2014-03-06 | 3.5 | x | x | x | x | Customer Meeting | Projektpräsentation (Datum?) Projektpräsentation - Inhalt: - Ergebnisse (Produktpräse) - Probleme & Lösungen - Next Steps - Lessons Learned Prototyp veröffentlichen Server zentral hosten Produktwebsite - Domain Studiduell kaufen - website designen (Inhalt: Blog, Downloadlink, Beschreibung - Fragen & Kategorien (Inhalt der App) - Login Appfunktionalität (Screen & Serveranbindung) | Maxi: Login & Register Funktionalität App & Duellanfrage & annehmen/ablehnen Ajax & Aktualisieren Button im Home Phil: Serveranbindung Rundenübersicht & Freund hinzufügen & Duell aufgeben Paul: NeuesSpiel & SpielerSuchen & URL & Port zentral speichern & Freund hinzufügen bei Spielersuche Kevin: Server zentral hosten, Fragenauswertung, logik Rundenbeginn/ende, 3 Fragen in verbleibender Kategorie erstellen, Server: Spiel aufgeben (Aufgeber = WartenAuf) --> bis EoB Dienstag 11.3